## GanttChart
Project 2 Schedule
CIVE 202
| Project Start Date | 2026-02-06 |  |  |  | Display Week | 2 |  | Week 2 | [6 empty] | Week 3 | [6 empty] | Week 4
| Project Lead | Schaefer Rogers | [6 empty] | 2026-02-09 | [6 empty] | 2026-02-16 | [6 empty] | 2026-02-23
[9 empty] | 2026-02-09 | 2026-02-10 | 2026-02-11 | 2026-02-12 | 2026-02-13 | 2026-02-14 | 2026-02-15 | 2026-02-16 | 2026-02-17 | 2026-02-18 | 2026-02-19 | 2026-02-20 | 2026-02-21 | 2026-02-22 | 2026-02-23 | 2026-02-24 | 2026-02-25 | 2026-02-26 | 2026-02-27 | 2026-02-28 | 2026-03-01
WBS | TASK | LEAD | PREDECESSOR | START | END | DAYS | % DONE | WORK DAYS | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S
1 | Project Management
1.1 | Scope of work | Anthony |  | 2026-02-11 | 2026-02-20 | 10 | 10% | 8
1.2 | Gnatt chart | Ava |  | 2026-02-11 | 2026-02-12 | 2 | 100% | 2
2 | Python Code
2.1 | Translate the Excel Logic into Python | Tu |  | 2026-02-13 | 2026-02-18 | 6 | 50% | 4
2.2 | Implement Sequential User Inputs | Ava |  | 2026-02-16 | 2026-02-20 | 5 | 0% | 5
2.3 | Generate a Final Mix Design Output | Schaefer |  | 2026-02-19 | 2026-02-20 | 2 | 0% | 2
2.4 | Prepare and Evaluate Four Concrete Mix Scenarios | All |  | 2026-02-13 | 2026-02-20 | 8 | 0% | 6
3 | Technical Implementation - Dependent on Code
3.1 | Mix scenarios research and documentation | Tu |  | 2026-02-16 | 2026-02-20 | 5 | 0% | 5
3.2 | Final Python code | Schaefer |  | 2026-02-16 | 2026-02-20 | 5 | 10% | 4
3.3 | Annotated code document | Anthony |  | 2026-02-19 | 2026-02-21 | 3 | 0% | 2
4 | Written Technical Report - Dependent on Code
4.1 | Introduction/SOW | Anthony |  | 2026-02-11 | 2026-02-20 | 10 | 10% | 8
4.2 | Methods | Tu |  | 2026-02-19 | 2026-02-22 | 4 | 0% | 2
4.3 | Results and discussion | Ava |  | 2026-02-19 | 2026-02-22 | 4 | 0% | 2
4.4 | Refrences | All |  | 2026-02-19 | 2026-02-22 | 4 | 0% | 2
5 | GitHub - Dependent on ALL
5.1 | GitHub | Schaefer |  | 2026-02-20 | 2026-02-23 | 4 | 0% | 2
Note on A7: Work Breakdown Structure Level 1: 1, 2, 3, ... Level 2: 1.1, 1.2, 1.3, ... Level 3: 1.1.1, 1.1.2, 1.1.3, … - The WBS uses a formula to control the numbering, but the formulas are different for different levels. Copy and Paste the cells in the WBS column from the examples at the bottom of the worksheet.
Note on B7: Task Description Enter the name of each task and sub-task. Use indents for sub-tasks.
Note on C7: Task Lead Enter the name of the Task Lead in this column.
Note on D7: Predecessor Tasks: You can use this column to enter the WBS of a predecessor for reference. The PRO version uses formulas to automatically calculate the Start Date based on the Predecessor.
Note on E7: Task Start Date You can manually enter the Start Date for each task or use a formula to create a dependency on a Predecessor. For example, you could enter =enddate+1 to set the Start date to the next calendar day, or =WORKDAY(enddate,1) to set the Start date to the next work day (excluding weekends), where enddate is the cell reference for the End date of the Predecessor task.
Note on F7: End Date: The End Date is calculated based on the Start Date and the Calendar Days columns.
Note on G7: Duration (Calendar Days) The duration is the number of calendar days for the given task. The duration is calculated as the End Date minus the Start Date plus 1 day, so that a task starting and ending on the same day has a duration of 1 day. Note: The conditional formatting used to create the gantt chart references this column.
Note on H7: Percent Complete Update the status of this task by entering the percent complete (between 0% and 100%).
Note on I7: Work Days Counts the number of work days, excluding the weekends (Saturday and Sunday). In the PRO version, you can customize the work week and list specific non-working days like holidays. In the PRO version, the default input is the Work Days instead of the Calendar Days.